## Sheet1
| ACTIVITY |  |  | ASSIGNED TO | DEPENDENCY | START DATE | DEADLINE DATE | PROJECT DURATION | DAYS PASSED FROM START DATE | DAYS LEFT TO DEDALINE | Timeline Progress | STATUS
Project/BCAC Phase | Planning |  |  |  |  | 2025-03-08 | 2025-04-01 | 24 | 140 | DONE | 100% | COMPLETED
Task | Identify the pain points | Analysis | Identify the pain points |  |  | 2025-03-01 | 2025-04-01 | 31 | 147 | DONE | 100% | COMPLETED
SUB TASK | Define the problem |  | Define the problem |  |  | 2025-03-01 | 2025-04-01 |  |  |  |  | AT RISK
SUB TASK | Conduct gap analysis |  | Conduct gap analysis |  |  | 2025-03-01 | 2025-04-01 | 31 | 147 | OVERDUE | 100% | DELAYED
SUB TASK | Study the situation |  | Study the situation |  |  | 2025-03-02 | 2025-04-02 | 31 | 146 | OVERDUE | 100% | ON TIME
Project/BCAC Phase | Planning |  |  |  |  | 2025-03-08 | 2025-04-01 | 24 | 140 | DONE | 100% | COMPLETED
Task | Analysis | Analysis |  |  |  | 2025-03-01 | 2025-04-01 | 31 | 147 | DONE | 100% | COMPLETED
SUB TASK | Build a project plan (Use this document) establish milestones and measurable objectives |  | Build a project plan (Use this document) establish milestones and measurable objectives |  |  | 2025-03-01 | 2025-04-01 | 31 | 147 | OVERDUE | 100% | AT RISK
SUB TASK | 2. Determine if the directed or suggested action should be treated as a spike based on the speed of relevance |  | 2. Determine if the directed or suggested action should be treated as a spike based on the speed of relevance |  |  | 2025-03-01 | 2025-04-01 | 31 | 147 | OVERDUE | 100% | DELAYED
TASK | BCAC_Phase_1_Validate_Request_Type |  |  |  |  | 2025-09-07 | 2025-09-17 | 10 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 1. Determine if the business problem is sufficiently similar to one previously vetted and solved (T-0) |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | DELAYED
SUB TASK | 1.1. Yes (Type 1) – Decide if the requested item will be used to solve a problem sufficiently similar to what the service was created for. If no, then change the request to Type 2 or Type 3 |  |  |  |  | 2025-03-01 | 2025-03-31 | 30 | 147 | OVERDUE | 100% | ON GOING
SUB TASK | 1.2 Yes (Type 2 and Type 3 ) - Change Type 2 or Type 3 requests to Type 0 or 1 and direct initiator to the corresponding solution |  |  |  |  | 2025-09-10 | 2025-09-15 | 5 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 1.3 No (all types) – Continue on to the next action as either a Type 2 or Type 3 solution |  |  |  |  | 2025-09-10 | 2025-09-15 | 5 | Not Started | 51 | 0% | DELAYED
TASK | BCAC_Phase_1_Elaborate_the_Capability_Need |  |  |  |  | 2025-08-17 | 2025-09-15 | 29 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 1. Develop/refine the concise business problem statement and desired end state (T-1 |  |  |  |  | 2025-08-17 | 2025-09-15 | 29 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 2. Validate the need supports a business outcome aligned with Business Enterprise Architecture (BEA), BMA Strategy and Functional Strategies (T-1) |  |  |  |  | 2025-08-17 | 2025-09-15 | 29 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 3. Analyze other organizations with similar capability needs to see if acceptable solutions already exist (T-0 |  |  |  |  | 2025-08-17 | 2025-09-15 | 29 | Not Started | 51 | 0% | LATE
SUB TASK | 4. Define the operational impact of the business problem if not addressed, in business terms |  |  |  |  | 2025-08-25 | 2025-09-15 | 21 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 5. Understand relevant laws, regulations, and policies (LRP) which constrain the solutio |  |  |  |  | 2025-08-29 | 2025-09-15 | 17 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 6. Make an initial determination if enhancement or new capability is likely to generate an Auditable Financial Transaction (AFT |  |  |  |  | 2025-08-29 | 2025-09-15 | 17 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 7. Define quantitative capability performance measures (target & threshold) and determine current values |  |  |  |  | 2025-08-29 | 2025-09-15 | 17 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 8. Identify and prioritize future business capabilities (including changes to existing capability) to solve the problem across DOT_LF-P (T-1 |  |  |  |  | 2025-08-29 | 2025-09-15 | 17 | Not Started | 51 | 0% | NOT STARTED
TASK | BCAC_Phase_1_Identify_Potential_Bill_Payers |  |  |  |  | 2025-08-17 | 2025-09-15 | 29 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 1. Identify potential bill payers to fund the need in the current year, execution plan, and POM |  |  |  |  | 2025-10-02 | 2025-11-15 | 44 | Not Started | 112 | 0% | NOT STARTED
TASK | BCAC_Phase_1_ATP_1 |  |  |  |  | 2025-08-05 | 2025-09-15 | 41 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 1. Make ATP 1 (Authority to Proceed) decision to Phase 2 |  |  |  |  | 2025-08-05 | 2025-09-15 | 41 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 1.1. BCAT I - Coordinate ATP 1 decision package through FPRG and FPB to the SEC |  |  |  |  | 2025-08-07 | 2025-09-15 | 39 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 1.2. Obtain OSD ATP 1 decision |  |  |  |  | 2025-08-09 | 2025-09-15 | 37 | Not Started | 51 | 0% | NOT STARTED
Project/BCAC Phase | BCAC_Phase_2 |  |  |  |  | 2025-08-01 | 2025-09-15 | 45 | Not Started | 51 | 0% | ON GOING
TASK | BCAC_Phase_2_Determine_PM_and_MDA |  |  |  |  | 2025-08-01 | 2025-09-15 | 45 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 1. Determine if PEO BES has sufficient resources to assign a Program Manager for this need at the speed of relevance |  |  |  |  | 2025-08-01 | 2025-09-15 | 45 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 1.1. If No - Route to BMA PRG for COA (e.g. augment PEO BES, reprioritize BES backlog, allow non-PEO BES Program Manager/MDA) |  |  |  |  | 2025-08-05 | 2025-09-15 | 41 | Not Started | DONE | 0% | COMPLETED
TASK | BCAC_Phase_2_Refine_Tailored_CIP |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | ON GOING
SUB TASK | 1. Develop/Update tailored Capability Implementation Plan (CIP) to meet the need (T-1 |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 2. Identify the high-level business processes that need to be improved to address the business problem (BPR) (T-0) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 3. Develop a high-level process map to be included in the Capability Process Maps (As-Is State, BPR) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 4. Conduct initial market research of full DOTMLPF-P including research of other organizations, other services USG with similar capabilities (BPR) (T-0) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | DELAYED
SUB TASK | 6. Develop a re-engineered to-be process with information assets, including best practices from BEA & AF process libraries (BPR) (T-1 |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 7. If needed, conduct prototyping to support process engineering and redesign of the future state (BPR) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 8. Provide technical assessment of proposed market research solutions (T-1) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | DELAYED
SUB TASK | 10. Establish business performance measures that will indicate when the process is being executed as intended (T-1) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 11. In coordination with the CDO, determine data management requirements (including authoritative data sources) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 12. Assess potential infrastructure impact, shared services needs, cybersecurity overlays, and platform requirements |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | DELAYED
SUB TASK | 13. Identify desired/required capabilities that the proposed solution cannot provide |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 13.1. If Capabilities Missing - Determine alternative Courses of Action (COAs) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 14. Identify and prioritize DOT_PF-P actions required to move the current process to the future process (Roadmap) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 15. As necessary, decompose and schedule the work through the next ATP |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | DELAYED
SUB TASK | 17. Identify likely bill payers for an initial funding plan to resource the need with Current Year offsets, execution plan changes and POM commitment |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 18. Conduct a cost-benefit analysis (including cost savings or avoidance from sunsetting and/or consolidation) |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 19. Establish affordability targets for business system with a compelling business case for committing organization resources |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | DELAYED
SUB TASK | 21. Determine what Airmen and processes could be impacted by the proposed change |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 22. Ensure funding is available for phase activities and provide funding plan for future phases |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | PENDING
SUB TASK | 22.1. If Not Available - Determine alternative COA |  |  |  |  | 2025-09-12 | 2025-09-15 | 3 | Not Started | 51 | 0% | DELAYED
TASK | BCAC_Phase_2_Breakdown_ATP_2 |  |  |  |  | 2025-08-18 | 2025-09-15 | 28 | Not Started | 51 | 0% | NOT STARTED
SUB TASK | 1. Make ATP 2 decisions (including approval of tailored path approval through ATP 3 to ATP 4) (T-0) |  |  |  |  | 2025-09-18 | 2025-09-25 | 7 | Not Started | 61 | 0% | NOT STARTED
SUB TASK | 1.1. BCAT III - ROM < $1M over FYDP |  |  |  |  | 2025-09-25 | 2025-09-30 | 5 | Not Started | 66 | 0% | NOT STARTED
SUB TASK | 1.2. BCAT II, and BCAT III - ROM> $1M over FYDP |  |  |  |  | 2025-10-01 | 2025-10-10 | 9 | Not Started | 76 | 0% | NOT STARTED
SUB TASK | 1.3. BCAT I - Coordinate ATP 2 decision package through Functional PRG and Functional PB to SEC |  |  |  |  | 2025-10-10 | 2025-10-15 | 5 | Not Started | 81 | 0% | NOT STARTED
SUB TASK | 3. Decision to Proceed with only non-Materiel Solution |  |  |  |  | 2025-10-01 | 2025-10-10 | 9 | Not Started | 76 | 0% | NOT STARTED
Project/BCAC Phase | BCAC_Phase_3 |  |  |  |  | 2025-08-25 | 2025-10-30 | 66 | Not Started | 96 | 0% | ON GOING
TASK | BCAC_Phase_3_Initiate_Acquisition_Planning |  |  |  |  | 2025-09-15 | 2025-09-20 | 5 | Not Started | 56 | 0% | ON GOING
SUB TASK | 1. Initiate and manage planning activities to build a tailored Acquisition Plan (T-0) |  |  |  |  | 2025-09-15 | 2025-09-25 | 10 | Not Started | 61 | 0% | ON GOING
SUB TASK | 2. Understand user experience including potential empathy maps, customer journey, etc. |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | 56 | 0% | ON GOING
SUB TASK | 3. Explore alternatives (market research on COTS, GOTS, aPaaS, Legacy Enhancements, Custom Development) via BEA and others |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 4. Consider if the AF "software factories" (i.e., Kessel Run, etc..) may be able to provide a business solution |  |  |  |  | 2025-09-20 | 2025-09-30 | 10 | Not Started | 66 | 0% | NOT STARTED
SUB TASK | 6. Conduct risk analysis and score alternatives against the evaluation criteria (T-0) |  |  |  |  | 2025-09-15 | 2025-09-25 | 10 | Not Started | 61 | 0% | ON GOING
SUB TASK | 7. Identify and recommend solution & approach for implementation of the business system (T-2) |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | 56 | 0% | ON GOING
SUB TASK | 8. Update the CIP's acquisition and solution strategies with planned decision points and authorities (T-0) |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 9. Elaborate non-materiel elements into executable DOT_LPF-P actions (T-0) |  |  |  |  | 2025-09-20 | 2025-09-30 | 10 | Not Started | 66 | 0% | NOT STARTED
SUB TASK | 11. Engage stakeholders on changes to schedule, scope or cost |  |  |  |  | 2025-09-20 | 2025-09-30 | 10 | Not Started | 66 | 0% | NOT STARTED
TASK | BCAC_Phase_3_Document_Business_Feature_Backlog |  |  |  |  | 2025-10-01 | 2025-10-30 | 29 | Not Started | 96 | 0% | NOT STARTED
SUB TASK | 1. Determine any service-specific or unique infrastructure requirements (to include Mobile Apps) (T-1) |  |  |  |  | 2025-09-15 | 2025-09-25 | 10 | Not Started | 61 | 0% | ON GOING
SUB TASK | 2. Collaboratively identify and capture features to deliver initial and subsequent business value to the customer (T-1) |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | 56 | 0% | ON GOING
SUB TASK | 3. Confirm potential business system solutions reflect traceability to features valued by the customer (T-0) |  |  |  |  | 2025-09-20 | 2025-09-30 | 10 | Not Started | 66 | 0% | NOT STARTED
SUB TASK | 4. Analyze features based on cost/benefit analysis |  |  |  |  | 2025-09-15 | 2025-09-25 | 10 | Not Started | 61 | 0% | ON GOING
SUB TASK | 5. Ensure potential business system includes trade space to minimize customization |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | 56 | 0% | ON GOING
SUB TASK | 6. Seek comments from identified stakeholders on features and initial prioritization |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 7. Establish the business value of each feature and create an initial point estimate for overall epic |  |  |  |  | 2025-09-15 | 2025-09-25 | 10 | Not Started | 61 | 0% | ON GOING
SUB TASK | 8. Identify potentially expensive or high-risk functional requirements with recommended alternate approaches |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | 56 | 0% | ON GOING
SUB TASK | 9. Approve or reject features based on cost/benefit analysis |  |  |  |  | 2025-09-20 | 2025-09-30 | 10 | Not Started | 66 | 0% | NOT STARTED
SUB TASK | 10. Place features in the parking lot or close, providing justification for feature status |  |  |  |  | 2025-09-15 | 2025-09-25 | 10 | Not Started | 61 | 0% | ON GOING
SUB TASK | 11. As needed, update business processes to reflect any changes made |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | 56 | 0% | ON GOING
SUB TASK | 12. Create an initial prioritization of features |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 13. Update the CIP's non-materiel elements (T-0) |  |  |  |  | 2025-09-20 | 2025-09-30 | 10 | Not Started | 66 | 0% | NOT STARTED
TASK | BCAC_Phase_3_Document_Report_Features |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | NOT STARTED
[6 empty] | 2025-03-01 | 2025-03-01
SUB TASK | 1. Define/update users of service's reporting features |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | NOT STARTED
[6 empty] | 2025-03-01 | 2025-03-01
SUB TASK | 2. Define/update user roles and responsibilities for the service's reporting features |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | NOT STARTED
[6 empty] | 2025-03-01 | 2025-03-01
SUB TASK | 3. Define/update access rights and access plan for users |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | NOT STARTED
[6 empty] | 2025-03-01 | 2025-03-01
TASK | BCAC_Phase_3_Document_Infrastructure_Features |  |  |  |  | 2025-09-15 | 2025-09-20 | 5 | Not Started | 56 | 0% | ON GOING
SUB TASK | 1. Determine any service-specific or unique infrastructure requirements (to include Mobile Apps) (T-1) |  |  |  |  | 2025-09-15 | 2025-09-25 | 10 | Not Started | 61 | 0% | ON GOING
SUB TASK | 2. Identify appropriate hosting solution (mil/commercial cloud, on-premise) (T-1) |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | 56 | 0% | ON GOING
SUB TASK | 3. Determine environments and tools for DevSecOps to support Agile execution as needed |  |  |  |  | 2025-09-17 | 2025-09-20 | 3 | Not Started | DONE | 0% | COMPLETED
SUB TASK | 4. Determine shared services as needed |  |  |  |  | 2025-09-20 | 2025-09-30 | 10 | Not Started | 66 | 0% | NOT STARTED
TASK | BCAC_Phase_3_Document_Service_Level_Features |  |  |  |  | 2025-10-01 | 2025-10-30 | 29 | Not Started | 96 | 0% | NOT STARTED
SUB TASK | 1. Define/update desired service outcomes with Key Performance Indicators (KPIs) from the customer viewpoint |  |  |  |  | 2025-10-01 | 2025-10-15 | 14 | Not Started | 81 | 0% | NOT STARTED
SUB TASK | 2. Identify customer and other key stakeholders to involve in Service Line Requirements (SLR), Service Line Agreement (SLA), Ops Line Agreement (OLA) Negotiations |  |  |  |  | 2025-10-01 | 2025-10-30 | 29 | Not Started | 96 | 0% | NOT STARTED
SUB TASK | 3. Draft requirements for services and mediate conflicting components |  |  |  |  | 2025-10-07 | 2025-10-30 | 23 | Not Started | 96 | 0% | NOT STARTED
TASK | BCAC_Phase_3_Document_Operational_COOP_Features |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | NOT STARTED
[6 empty] | 2025-03-01 | 2025-03-01
SUB TASK | 1. Define/update COOP/ Monitoring requirements for service (T-1) |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | NOT STARTED
[6 empty] | 2025-03-01 | 2025-03-01
SUB TASK | 2. Analyze against current COOP/Monitoring |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | NOT STARTED
[6 empty] | 2025-03-01 | 2025-03-01
SUB TASK | 3. Determine system monitoring tools and plan for new service and systems (T-1) |  |  |  |  | 2025-03-01 | 2025-03-01 | 0 | 147 | OVERDUE | 0% | NOT STARTED
[6 empty] | 2025-03-01 | 2025-03-01
Formulas:
DAYS PASSED FROM START DATE = IF(OR([ACTIVITY]="",[START DATE]="",[DEADLINE DATE]=""),"",IF(TODAY()-[START DATE]<0,"Not Started",TODAY()-[START DATE]))
DAYS PASSED FROM START DATE = IF(OR(C5="",[START DATE]="",[DEADLINE DATE]=""),"",IF(TODAY()-[START DATE]<0,"Not Started",TODAY()-[START DATE]))
DAYS LEFT TO DEDALINE = IF([STATUS]="COMPLETED","DONE",IF(IF(OR([ACTIVITY]="",[START DATE]="",[DEADLINE DATE]=""),"",[DEADLINE DATE]-TODAY())<=0,"OVERDUE",IF(OR([ACTIVITY]="",[START DATE]="",[DEADLINE DATE]=""),"",[DEADLINE DATE]-TODAY())))
DAYS LEFT TO DEDALINE = IF([STATUS]="COMPLETED","DONE",IF(IF(OR(C5="",[START DATE]="",[DEADLINE DATE]=""),"",[DEADLINE DATE]-TODAY())<=0,"OVERDUE",IF(OR(C5="",[START DATE]="",[DEADLINE DATE]=""),"",[DEADLINE DATE]-TODAY())))